## Sheet1
Project Name |  | Orthocare
Project Start Date |  | 2023-12-14
Project Estimated End Date |  | 2023-12-18
Project Actual End Date
Project SEO Objective (if any) | [PCD,Franchise,Third Party,Special] | [7 empty] | PCD
Project Type (Laravel/React/Wordpress) |  | Laravel | [6 empty] | Franchise
Third Party
Phase 1 Requirements Phase | [7 empty] | 3 days max | Special
|  |  | In Progress | Done | Status Date | Task Start Date | Task End Date | Estimated Time
Template
Creation of template
Publishing of template
Choose on Internet
Changes in choosen
Deployment Details of Existing Server (if any)
Mysql Version
PHP Version
Content for About Page
Content
Images
Content for Product Page
| Content | [8 empty] | Select
| Images | [8 empty] | Yes
No
Content on Contact Page
Social Media Details
Map coordinates
Email and Phone Details
Content for Categories
Content
Images
Content for Blog Page
Content
Images
Search Function Page
Enquiry Form
Ajax Based
Basic Form
Thanks Page
Image
Coding Decision
Code Reuse
Code Writing
Versioning
Provision for subdomain for client reviewal
Phase 2 Development Phase
DB Design | [7 empty] | Basis: Specs
Code Writing | [7 empty] | Basis: Specs
Template merging | [7 empty] | 15 hours max
Code Changes | [7 empty] | 10 hours max
Admin Data Entry | [7 empty] | Basis: Data Amount
Client Reviewal Deployment Setup | [7 empty] | 3 hours max
Seo code deployment for indexing, tracking etc | [7 empty] | Basis: Seo Team
Phase 3 Testing Phase | [7 empty] | 10 hours max
Basics
Check for broken links
Spelling and Grammer
Browser compatibility or Responsive
Performance
Google page speed checks
Optimize http headers
Image optimization
Usability
404 Error Handling
Slug checking
Favicon
Print friendly CSS checks
Paging
Mail sender address
Mail sender name
SEO related developer work
Sitemap Generation
Google snippets
Meta tags
Robots.txt file changes
HTML attributes check for SEO
1. Breadcrums in H1 tags
2. Alt Tags
3. Home page should have H1 tag
Code Quality
HTML Validations
Form Validations
Mail Checks
Admin Panel Testing
Browser based errors final checks
Phase 4 Customer Reviewal
Changes Requests by Client
Approval at Management level
Back to Developer Phase
Phase 5 Deployment Phase
Deployment on Actual Server
Seo code deployment for indexing, tracking etc
Note on B29: This details is required from client and also footer text.